## Team1_Estimated_Effort
Task Name: (Dependencies top to bottom) | [8 empty] | Austin | Mark | Mohammad | Raymond | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task
Preliminary &
Parallel Tasks | Architecture |  |  |  |  | 3 |  | 0
|  | Design architecture | Project Manager | Mark | 3 | [7 empty] | 0
| Requirements |  |  |  |  | 6 |  | 0 |  |  |  |  | 0
|  | Gather | Requirements Engineer | Austin | 2 | [7 empty] | 0
|  | Analyze | Requirements Engineer | Austin | 2 | [7 empty] | 0
|  | Specify | Requirements Engineer | Austin | 2 | [7 empty] | 0
| Documentation |  |  |  |  | 11 |  | 0 |  |  |  |  | 0
|  | Project Charter | Project Manager | Mark | 1 | [7 empty] | 0
|  | Release Plan | Project Manager | Mark | 1 | [7 empty] | 0
|  | Requirements Document | Project Manager, Requirements Engineer | Mark, Austin | 1 | [7 empty] | 0
|  | Project Plan | Project Manager, Developers | Mark, Austin, Raymond, Mohammad | 2 | [7 empty] | 0
|  | Architecture Document | Architect | Mohammad | 2 | [7 empty] | 0
|  | Test Report | Tester | Raymond | 1 | [7 empty] | 0
|  | User Guide & System Admin Doc | Developers, Requirements Engineer | Mark, Austin, Raymond, Mohammad | 3 | [7 empty] | 0
Coding | [6 empty] | 0 | [5 empty] | 0
Iteration 1: | Development |  |  |  |  | 23 |  | 0 |  |  |  |  | 0
|  | Determine technology needs | Developer | Austin | 1 | [7 empty] | 0
|  | Research web application development | Developer | Mark, Raymond | 5 | [7 empty] | 0
|  | Design inital Algorithm | Developer | Austin, Mohammad | 3 | [7 empty] | 0
|  | Implement classes | Developer | Austin, Mohammad | 5 | [7 empty] | 0
|  | Create simple testing GUI | Developer | Mark, Raymond | 3 | [7 empty] | 0
|  | Write code for managing HTTP session | Developer | Mark, Raymond | 4 | [7 empty] | 0
|  | Unit Testing | Developer, Tester | Raymond | 2 | [7 empty] | 0
| Analysis |  |  |  |  | 6 |  | 0 |  |  |  |  | 0
|  | System Testing | Tester | Raymond | 2 | [7 empty] | 0
|  | Bug fix as required | Tester, Developer | Raymond | 2 | [7 empty] | 0
|  | Evaluate needs for next iteration | Project Manager | Mark | 2 | [7 empty] | 0
Iteration 2: | Design |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
|  | Implement any design changes | Project Manager | [9 empty] | 0
|  | Risk analysis | Project Manager | [9 empty] | 0
|  | Design XML format | Developer | [9 empty] | 0
|  | Design Perl XML-handling code | Developer | [9 empty] | 0
|  | Create UI design for balance screen | Developer | [9 empty] | 0
| Development |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
|  | Review requirements | Developer | [9 empty] | 0
|  | Create XML parsing code | Developer | [9 empty] | 0
|  | Handle XML data structure for retrieving balance | Developer | [9 empty] | 0
|  | Implement UI | Developer | [9 empty] | 0
|  | Unit Testing | Developer | [9 empty] | 0
| Analysis |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
|  | System Testing | Tester | [9 empty] | 0
|  | Bug fix as required | Tester, Developer | [9 empty] | 0
|  | Evaluate needs for next iteration | Project Manager | [9 empty] | 0
Iteration 3: | Design |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
|  | Implement any design changes | Project Manager | [9 empty] | 0
|  | Risk analysis | Project Manager | [9 empty] | 0
|  | Create UI design for vendor locations | Developer | [9 empty] | 0
|  | Design data structure for RSS location list | Developer | [9 empty] | 0
| Development |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
|  | Review requirements | Developer | [9 empty] | 0
|  | Develop code for processing vendor locations | Developer | [9 empty] | 0
|  | Implement vendor map display | Developer | [9 empty] | 0
|  | Display vendor information | Developer | [9 empty] | 0
|  | Unit Testing | Developer | [9 empty] | 0
| Analysis |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
|  | Acceptance Testing | Tester, Project Manager | [9 empty] | 0
|  | Bug fix as required | Tester, Developer | [9 empty] | 0
Total |  |  |  |  | 49 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0