## Team1_Estimated_Effort
Task Name: (Dependencies top to bottom) | [8 empty] | Austin | Blake | Mark | Mohammad | Raymond | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task | By Task
Preliminary &
Parallel Tasks | Architecture |  |  |  |  | 3 |  | 1
|  | Design architecture | Project Manager | Mark | 3 |  | 1 |  |  |  | 1 |  |  | 1
| Requirements |  |  |  |  | 6 |  | 3 | [5 empty] | 0
|  | Gather | Requirements Engineer | Austin | 2 |  | 1 |  | 1 |  |  |  |  | 1
|  | Analyze | Requirements Engineer | Austin | 2 |  | 1 |  | 1 |  |  |  |  | 1
|  | Specify | Requirements Engineer | Austin | 2 |  | 1 |  | 1 |  |  |  |  | 1
| Documentation |  |  |  |  | 8 |  | 14 | [5 empty] | 0
|  | Project Charter | Project Manager | Mark | 1 |  | 2 |  |  |  | 2 |  |  | 2
|  | Release Plan | Project Manager | Mark | 1 |  | 2 |  |  |  | 2 |  |  | 2
|  | Requirements Document | Project Manager, Requirements Engineer | Mark, Austin | 1 |  | 4 |  | 2 |  | 2 |  |  | 4
|  | Project Plan | Project Manager, Developers | Mark, Austin, Raymond, Mohammad | 2 |  | 5 |  | 1 | 1 | 1 | 1 | 1 | 5
|  | Architecture Document | Architect | Mohammad | 2 |  | 0 | [6 empty] | 0
|  | Test Report | Tester | Raymond | 1 |  | 1 | [5 empty] | 1 | 1
Coding | [6 empty] | 0 | [6 empty] | 0
Iteration 1: | Development |  |  |  |  | 25 |  | 15 | [5 empty] | 0
|  | Determine technology needs | Developer | Austin | 1 |  | 1 |  | 1 |  |  |  |  | 1
|  | Research web application development | Developer | Mark, Blake | 5 |  | 5 |  |  | 3 | 2 |  |  | 5
|  | Design initial Algorithm | Developer | Austin, Mohammad | 3 |  | 0 | [6 empty] | 0
|  | Implement classes | Developer | Austin, Mohammad | 5 |  | 0 | [6 empty] | 0
|  | Create simple testing GUI | Developer | Mark, Raymond | 3 |  | 2 | [5 empty] | 1 | 1
|  | Model Architecture | Developer | Raymond, Blake | 2 |  | 2 |  |  | 2 |  |  | 1
|  | Write code for managing HTTP session | Developer | Raymond, Blake | 4 |  | 4 |  |  | 2 |  |  | 2 | 4
|  | Unit Testing | Developer, Tester | Raymond | 2 |  | 1 | [5 empty] | 1 | 1
| Analysis |  |  |  |  | 6 |  | 2 | [5 empty] | 0
|  | System Testing | Tester | Raymond | 2 |  | 0 | [6 empty] | 0
|  | Bug fix as required | Tester, Developer | Raymond | 2 |  | 1 | [5 empty] | 1 | 1
|  | Evaluate needs for next iteration | Project Manager | Mark | 2 |  | 1 |  |  |  | 1 |  |  | 1
Iteration 2: | Design |  |  |  |  | 15 |  | 16 | [5 empty] | 0
|  | Implement any design changes | Project Manager | Mark | 3 |  | 1 |  |  |  | 1 |  |  | 1
|  | Risk analysis | Project Manager | Mark | 2 |  | 2 |  |  |  | 2 |  |  | 2
|  | Design Web Architecture | Developer | Blake, Raymond | 3 |  | 5 |  |  | 4 |  |  | 1 | 5
|  | Design and Refine Algorithm | Developer | Mohammad, Austin | 5 |  | 6 |  | 6 |  |  |  |  | 6
|  | Prototype GUI | Developer | Mark, Raymond | 2 |  | 2 | [5 empty] | 1 | 1
| Development |  |  |  |  | 17 |  | 18 | [5 empty] | 0
|  | Review requirements | Developer | Everyone | 2 |  | 6 |  | 2 |  | 2 |  | 2 | 6
|  | Implement Web Architecture | Developer | Blake, Raymond | 5 |  | 5 |  |  | 4 |  |  | 2 | 6
|  | Convert Algorithm into Javascript | Developer | Mohammad, Austin | 3 |  | 3 |  | 3 |  |  |  |  | 3
|  | Implement GUI | Developer | Mark, Blake | 5 |  | 2 |  |  | 2 |  |  |  | 2
|  | Unit Testing | Developer | Raymond | 2 |  | 2 | [5 empty] | 2 | 2
| Analysis |  |  |  |  | 6 |  | 3 | [5 empty] | 0
|  | System Testing | Tester | Raymond | 2 |  | 1 | [5 empty] | 1 | 1
|  | Bug fix as required | Tester, Developer | Raymond | 2 |  | 1 | [5 empty] | 1 | 1
|  | Evaluate needs for next iteration | Project Manager | Mark | 2 |  | 1 |  |  |  | 1 |  |  | 1
Iteration 3: | Design |  |  |  |  | 7 |  | 3 | [5 empty] | 0
|  | Implement any design changes | Project Manager | Mark | 1 |  | 1 |  |  |  | 1 |  |  | 1
|  | Risk analysis | Project Manager | Mark | 2 |  | 1 |  |  |  | 1 |  |  | 1
|  | Design and Implement Database | Developer | Austin | 4 |  | 1 |  | 1 |  |  |  |  | 1
| Development |  |  |  |  | 13 |  | 15.5 | [5 empty] | 0
|  | Refine Algorithm to handle non-hourly times | Developer | Austin, Mohammad | 2 |  | 4 |  | 4 |  |  |  |  | 4
|  | Refine GUI | Developer | Blake | 3 |  | 5 |  |  | 5 |  |  |  | 5
|  | Link Algorithm, GUI, and Database | Developer | Blake | 2 |  | 1.5 |  |  | 2 |  |  |  | 2
|  | Implement Database Security | Developer | Raymond, Mark | 3 |  | 3 | [5 empty] | 1.5 | 1.5
|  | Unit Testing | Developer | Austin | 3 |  | 2 |  | 2 |  |  |  |  | 2
| Analysis |  |  |  |  | 4 |  | 5 | [5 empty] | 0
|  | Acceptance Testing | Tester, Project Manager | Mark, Raymond | 2 |  | 2 |  |  |  | 2 |  | 1 | 3
|  | Bug fix as required | Tester, Developer | Raymond | 2 |  | 3 | [5 empty] | 3 | 3
Iteration 4 | Design |  |  |  |  | 5 |  | 0
|  | Implement any design changes | Project Manager | Mark | 1 | [8 empty] | 0
|  | Risk analysis | Project Manager | Mark | 2 | [8 empty] | 0
|  | Design and Implement Database | Developer | Austin | 2 | [8 empty] | 0
| Development |  |  |  |  | 16 |  | 0
|  | Refine Algorithm | Developer | Austin | 4 | [8 empty] | 0
|  | Refine GUI | Developer | Blake | 4 | [8 empty] | 0
|  | Create SQLite Database | Developer | Blake | 4 | [8 empty] | 0
|  | Link Database, GUI, and Algorithm | Developer | Blake, Austin, Raymond, Mark | 4 | [8 empty] | 0
| Analysis |  |  |  |  | 4 |  | 0
|  | Acceptance Testing | Tester, Project Manager | Raymond, Mohammad | 2 | [8 empty] | 0
|  | Bug fix as required | Tester, Developer | Austin, Raymond | 2 | [8 empty] | 0
Total |  |  |  |  | 135 | 135 | 95.5 | 95.5 | 25 | 25 | 21 | 1 | 23.5 | 95.5